## Sheet1
sno | Date | Task | Project | Hours | Status
1 | 2020-12-17 | Database structuring in duplicate project | Duplicate | 2 | Done
2 | 2020-12-17 | Changes in view and functionality according to database structuring | Duplicate | 2 | Done
3 | 2020-12-17 | Create rules of auditing | Duplicate | 2 | Ongoing
4 | 2020-12-17 | Understand companiesnext view functionality (templating) | CompaniesNex | 2 | Done
5 | 2020-12-18 | Create rules of auditing (functionality) | Duplicate | 3 | Done
6 | 2020-12-18 | Search Open source of HRMS (1 is shown on 16-Dec-2020) | HRMS | 1 | Done
7 | 2020-12-18 | Companies next review and code flow understanding | CompaniesNex | 2 | Ongoing
8 | 2020-12-18 | Testing of actfirst and whistlefirst by Deepak (feedback on whistlefirst is shared by Deepak) |  | 2 | Ongoing
9 | 2020-12-19 | Upload data in database | Duplicate | 4 | Done
10 | 2020-12-19 | Change in rules creation to apply on uploaded data | Duplicate | 2 | Done
11 | 2020-12-19 | Companies next review and code flow understanding | CompaniesNex | 2 | Ongoing
12 | 2020-12-21 | Valuation landing page v2 | Proxcel | 1 | Done
13 | 2020-12-21 | change in rules and mapping of columns | Duplicate | 2 | Done
14 | 2020-12-21 | Apply rules on uploaded data | Duplicate | 3 | Ongoing
15 | 2020-12-21 | Understand code functionality and report genearation | CompaniesNex | 2 | Done
16 | 2020-12-22 | Companies next code review | CompaniesNex | 4 | Done
17 | 2020-12-22 | Graphs layout understanding in report section | CompaniesNex | 4 | Ongoing
18 | 2020-12-23 | Companies next setup on our server | CompaniesNex | 3 | Ongoing | Database and files are upload by giving error because of server
19 | 2020-12-23 | Applying rules after removing delimeter | Duplicate | 5 | Ongoing
20 | 2020-12-23 | Companies next setup on our server | CompaniesNex | 2 | Done
21 | 2020-12-24 | add survey form in website | Whistlefirst | 3 | Done
22 | 2020-12-24 | Create regex to match data after removing special character | Duplicate | 5 | Ongoing
23 | 2020-12-26 | Purchase ssl certificate for rajgadhia.com and companiesnext.com |  |  | Done
24 | 2020-12-28 | Install ssl certificate on rajgadhia.com and companiesnext.com | 1 |  | Done
25 | 2020-12-29 | Regex created to match data after removing special character | Duplicate | 5 | Done
26 | 2020-12-29 | search on bulk email tool | Proxcel | 3 | Done
27 | 2020-12-30 | Create data set to match data from previous data | Duplicate | 8 | Ongoing
28 | 2020-01-31 | Create data set to match data from previous data | Duplicate | 5 | Ongoing
29 | 2021-01-01 | Work on bulk email tool so mail can't span |  | 3 | Done
30 | 2021-01-01 | show uploaded set data in table | Duplicate | 5 | Ongoing
31 | 2021-01-04 | show uploaded set data in table | Duplicate | 5 | Done
32 | 2021-01-05 | Match transactional data from histroic data | Duplicate | 8 | Ongoing
33 | 2021-01-06 | Match transactional data from histroic data | Duplicate | 8 | Ongoing
34 | 2021-01-07 | Match transactional data from histroic data | Duplicate | 8 | Ongoing
35 | 2021-01-08 | Match transactional data from histroic data | Duplicate | 8 | Ongoing
38 | 2021-01-11 | Match transactional data from histroic data | Duplicate | 8 | Ongoing
39 | 2021-01-12 | Match transactional data from histroic data | Duplicate | 8 | Ongoing
40 | 2021-01-13 | Match transactional data from histroic data | Duplicate | 8 | Done
41 | 2021-01-14 | Match transactional data from histroic data and with its own data set | Duplicate | 8 | Ongoing
42 | 2021-01-15 | Match transactional data from histroic data and with its own data set | Duplicate | 8 | Ongoing
43 | 2021-01-16 | Match transactional data from histroic data and with its own data set | Duplicate | 6 | Done
44 | 2021-01-16 | Show duplicate records in view | Duplicate | 3 | Ongoing
45 | 2021-01-18 | Show duplicate records in view | Duplicate | 5 | Done
46 | 2021-01-18 | Blogs folder and blogs tag redirection | CompaniesNext | 1 | Done
47 | 2021-01-18 | CompaniesNext google search redirection | CompaniesNext | 2 | Done
48 | 2021-01-19
| 2021-02-01 | search graphs for reports | CompaniesNext | 6.5 | Done
| 2021-02-01 | Call with chandan and lenskart | Actfirst | 1.5 | Done
| 2021-02-02 | Companies Next Report | CompaniesNext | 6 | Ongoing
| 2021-02-02 | Upload blog on companiesNext | CompaniesNext | 2 | Done
| 2021-02-03 | Make Password dynamic | Actfirst | 1.5 | Done
| 2021-02-03 | Reset Password | Actfirst | 1.5 | Done
| 2021-02-03 | Upload blog on companiesNext with proper formatting | CompaniesNext | 2 | Done
| 2021-02-03 | Make some desing changes in blog section | CompaniesNext | 3 | Ongoing
| 2021-02-04 | Report changes | CompaniesNext | 8 | Ongoing
| 2021-02-05 | Change in report font and spacing | CompaniesNext | 8 | Done
| 2021-02-06 | Change in report font and spacing | CompaniesNext | 8 | Done
| 2021-02-09 | Desigin professional report (HTML CSS) | CompaniesNext | 8 | Done
| 2021-02-10 | Put graphs and get real data in professional report | CompaniesNext | 8 | Ongoing | Done till financial performance
| 2021-02-11 | Make report data dyanmic | CompaniesNext | 8 | Ongoing
| 2021-02-12 | Make report data dyanmic | CompaniesNext | 6 | Done
| 2021-02-24 | Add sanitary page in website | Rajgadhia | 2 | Done
| 2021-02-24 | Add new page where to buy | Rajgadhia | 1 | Done
| 2021-02-24 | Add dropdown in where to buy page | Rajgadhia | 5 | Done
| 2021-02-25 | Create database for filters | Rajgadhia | 1 | Done
| 2021-02-25 | Create functionality to filter out dealaers on location basis | Rajgadhia | 7 | Done
| 2021-02-26 | Actfirst changes | Actfirst | 4 | Done
| 2021-02-26 | Create UI of b2c form in whistlefirst and submit data in database | Whistlefirst | 4 | Ongoing
| 2021-03-01 | Submit data to database and save uploaded attachment | Whistlefirst | 8 | Done
| 2021-03-02 | Work on B2c whistlefirst form | Whistlefirst | 8 | Ongoing
| 2021-03-03 | Change meta description, meta keywords and meta title in companiesNext | CompaniesNext | 2 | Done
| 2021-03-03 | Work on propages URL structure | CompaniesNext | 2 | Ongoing
| 2021-03-03 | Debug actfirst error faced by shail garg (lenskart) | Actfirst | 2 | Done
| 2021-03-03 | Add B2c complaint modal in homepage | Whistlefirst | 1 | Done
| 2021-03-03 | Show B2c complaint senior management details in admin panel | Whistlefirst | 1 | Done
| 2021-03-04 | Change propages url structure in companiesNext | CompaniesNext | 3 | Done
| 2021-03-04 | Add email in whistlefirst b2c form | Whistlefirst | 1 | Done
| 2021-03-04 | Add mail and telphone in companiesNext menu | CompaniesNext | 1 | Done
| 2021-03-04 | Add would you like to reach us out in column In b2c form | Whistlefirst | 1 | Done
| 2021-03-04 | Center align b2c modal on homepage | Whistlefirst | 1 | Done
| 2021-03-04 | Add functionality to remove add more senior management fields in b2c form | Whistlefirst | 1 | Ongoing
| 2021-03-05 | Add whatsapp link in companiesNext | CompaniesNext | 3 | Done
| 2021-03-05 | Add social links on companiesNext | CompaniesNext |  | Done
2021-03-08
| 2021-03-09 | Add review us on Proxcel, Whisltefirst
2021-03-10
2021-03-11
2021-03-12
| 2021-03-15 | Make change in Professional reports Graphs | CompaniesNext | 8 | Done
| 2021-03-16 | Apply condition for user to choose report (Professional and business users) | CompaniesNext | 8 | Ongoing
| 2021-03-17 | Correct year in profit loss page in DCF form | CompaniesNext | 8 | Ongoing
| 2021-03-18 | Resolve himushu's query from ncube logictics(phasing issue while uploading observation) | Actfirst | 3 | Done
| 2021-03-18 | Correct year in profit loss page in DCF form | CompaniesNext | 5 | Ongoing
| 2021-03-20 | Correct year in profit loss page in DCF form | CompaniesNext | 8 | Done
| 2021-03-21 | Make functional calculate button in dcf form | CompaniesNext | 4.5 | Done
| 2021-03-21 | DCF report data not coming properly in table | CompaniesNext | 3.5 | Ongoing
2021-03-22
2021-03-23
2021-03-24
| 2021-03-25 | Working on css issue | CompaniesNext | 8 | Ongoing
| 2021-03-26 | Working on css issue | CompaniesNext | 8 | Done
2021-03-30
| 2021-04-06 | Add transaction data dropdown in header | Duplicate Payment | 2 | Done
| 2021-04-06 | Add division, transaction dropdown while uploading transaction data | Duplicate Payment | 3 | Done
| 2021-04-06 | Map data with process division and transaction | Duplicate Payment | 3 | Ongoing
| 2021-04-07 | Mapping of data with process division and transaction | Duplicate Payment | 3 | Done
| 2021-04-07 | Add comment section box in both process manager and hod to add comment on duplicate records | Duplicate Payment | 2 | Done
| 2021-04-07 | Create approval mechanism to approve data is correctly verify by process manager | Duplicate Payment | 3 | Ongoing
| 2021-04-08 | Approval and reject mechanism to approve data is correctly verify by process manager | Duplicate Payment | 8 | Done
| 2021-04-09 | Put condition for showing comment box on audit page and differenate user on permission basis for audit and approve | Duplicate Payment | 8 | Ongoing
| 2021-04-12 | Put condition for showing comment box on audit page and differenate user on permission basis for audit and approve | Duplicate Payment | 8 | Done
| 2021-04-13 | Check user that it working for payment , invoice or for both | Duplicate Payment | 3 | Done
| 2021-04-13 | Put condition while adding division HOD | Duplicate Payment | 5 | Ongoing
| 2021-04-14 | Put condition while adding division HOD | Duplicate Payment | 2 | Done
| 2021-04-14 | Change in assingning permission to User (Process Manager or HOD) | Duplicate Payment | 4 | Done
| 2021-04-14 | show revenue and cost saving from tool on dashboard on HOD, Processmanager | Duplicate Payment | 2 | Ongoing
| 2021-04-15 | show revenue and cost saving from tool on dashboard on HOD, Processmanager | Duplicate Payment | 6 | Ongoing
| 2021-04-15 | Create UI for dashborad | Duplicate Payment | 2 | Done
| 2021-04-16 | create table in database for getting data for dashboard | Duplicate Payment | 30 min | Done
| 2021-04-16 | Create query to get data of potential and duplicate records to show on graphs | Duplicate Payment | 8 | Ongoing
| 2021-04-17 | Study about zend guard for encrypting of data |  | 2 | Done
| 2021-04-17 | Create query to get data of potential and duplicate records to show on graphs | Duplicate Payment | 4 | Done
| 2021-04-17 | Show data on graphs of potential and duplicate graph | Duplicate Payment | 2 | Ongoing
| 2021-04-19 | Show data on graphs of potential and duplicate graph | Duplicate Payment | 8 | Ongoing
| 2021-04-20 | Show data on graphs of potential and duplicate graph | Duplicate Payment | 8 | Ongoing
| 2021-04-21 | Show data on graphs of potential and duplicate graph (7 days) | Duplicate Payment | 5 | Done
| 2021-04-21 | Show data on graphs of potential and duplicate graph (month totol saving ) | Duplicate Payment | 3 | Done
| 2021-03-22 | Put condition on dashboard to show additional information to Lenskart | Actfirst | 4 | Done
| 2021-03-22 | Write a logic to calculate financial year for showing data according to financial year | Actfirst | 4 | Ongoing
| 2021-04-23 | Renew whistlefirst.com and whistlefirst.in domain |  | 30 | Done
| 2021-04-23 | Write a logic to calculate financial year for showing data according to financial year | Actfirst | 8 | Done
| 2021-04-26 | Get process of every process manager according to action plan | Actfirst | 8 | Done
| 2021-04-27 | Calculate actions according to financial years | Actfirst | 8 | Ongoing
| 2021-04-28 | Calculate actions according to financial years | Actfirst | 6 | Done
| 2021-04-28 | Show data according to financial years on UI | Actfirst | 2 | Ongoing
| 2021-04-29 | Show data according to financial years on UI | Actfirst | 8 | Done
| 2021-04-30 | Show data of open status according to financial year | Actfirst | 3 | Done
| 2021-04-30 | Show data according to crticality | Actfirst | 5 | Done
| 2021-05-01 | Add security from one company cannot access other company data if they know there id | Actfirst | 8 | Ongoing
| 2021-05-03 | Add security from one company cannot access other company data if they know there id(In Report and action plan) | Actfirst | 8 | Done
| 2021-05-04 | Add security from one company cannot access other company data if they know there id(In Report and action plan) Process Manager | Actfirst | 8 | Done
| 2021-05-05 | Check whistlefirst url from where one company access other company data by URL | Whistlefirst | 8 | Ongoing
| 2021-05-06 | show actions plans of process manager when admin click on numbers | Actfirst | 8 | Ongoing
| 2021-05-07 | show actions plans of process manager when admin click on numbers | Actfirst | 8 | Done